## Slide 1
ENGINEERING CORE
Project and Programme Management
Core topic 17
Specification reference: 17.1, 17.2, 17.3
Design and Development for Engineering and Manufacturing T Level · Lesson slides
Unofficial teaching resource. Check the official City & Guilds specification for assessment detail.

## Slide 2
ENGINEERING CORE · Core topic 17
Learning objectives
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
2
By the end of this lesson you should be able to:
1
Describe the project life cycle, constraints and risk management.
2
Describe project roles and responsibilities.
3
Plan a project using Gantt charts, CPA and PERT.
4
Monitor and control a project by stages and by exception.
STARTER
Building a bridge involves hundreds of tasks. How would you know which ones can't be allowed to slip?

## Slide 3
ENGINEERING CORE · Core topic 17
The project life cycle
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
3
1
Initiate
Brief, goals and success criteria.
2
Plan
Resources, schedule, risks.
3
Implement
Do the work.
4
Monitor
Track against the plan.
5
Report
Keep stakeholders informed.
6
Evaluate
Review and learn.
Notes: Constraints: budget, cost, quality, time, safety, resources, communication, reputation, changing requirements. Collaborative working includes matrix working and collaborative technologies.

## Slide 4
ENGINEERING CORE · Core topic 17
Roles
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
4
1
Stakeholders
Clients, regulators and others with an interest.
2
Project manager
Plans, monitors and controls the project.
3
Team members
Deliver the tasks and report progress.
4
Responsibilities
Communication, monitoring, planning, finance, reporting.

## Slide 5
ENGINEERING CORE · Core topic 17
Planning and control
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
5
Planning tools
Gantt charts: tasks on a timeline
Critical path analysis: the longest chain of dependent tasks
PERT: optimistic, likely and pessimistic estimates
Contingency planning and managing interdependencies
Control methods
Monitoring reports: budget, quality, cost, time
Managing by stages: approve each stage before the next
Managing by exception: escalate only when limits are exceeded

## Slide 6
ENGINEERING CORE · Core topic 17
Check your understanding
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
6
1
What happens if a critical path task is delayed?
2
What is managing by exception?
3
What does PERT use for time estimates?
4
Name three project constraints.
Notes: Give students a few minutes to answer on mini whiteboards or paper, then reveal the answers on the next slide.

## Slide 7
ENGINEERING CORE · Core topic 17
Answers
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
7
1
What happens if a critical path task is delayed?
The whole project is delayed.
2
What is managing by exception?
Only escalating issues when agreed tolerances are exceeded.
3
What does PERT use for time estimates?
Optimistic, most likely and pessimistic estimates.
4
Name three project constraints.
Any three, e.g. budget, time, quality.
Notes: Talk through any answers the class found difficult.

## Slide 8
ENGINEERING CORE · Core topic 17
Activity: Plan a workshop project
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
8
30 minutes
Pairs
1
Tasks: design (3 days), order parts (5), machine parts (4), assemble (2), test (1). Machining can't start until parts arrive.
2
Draw a Gantt chart.
3
Find the critical path and total duration.
4
Write one contingency plan.
SUCCESS CRITERIA
Dependencies correct
Critical path identified
Contingency is realistic
Notes: If ordering can start during design, the path is order, machine, assemble, test = 12 days; if it waits for design, 15 days. Discuss both.

## Slide 9
ENGINEERING CORE · Core topic 17
Exit ticket
1
Why involve regulators as stakeholders?
2
What is float?
3
When would you manage by stages?
REVISE THIS TOPIC
Revision notes for this lesson are on the study wiki:
Engineering Core, Part 2
https://lana6478.github.io/T-level-Design-Development-Engineering-Manufacturing/#/01-core-component/02-engineering-core-part2.md
Notes: Students answer on a sticky note or in the chat before leaving.