## Slide 1
ENGINEERING CORE
Project and Programme Management
Core topic 17
Specification reference: 17.1, 17.2, 17.3
Design and Development for Engineering and Manufacturing T Level · Lesson slides
Unofficial teaching resource. Check the official City & Guilds specification for assessment detail.

## Slide 2
ENGINEERING CORE · Core topic 17
Learning objectives
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
2
By the end of this lesson you should be able to:
1
Describe the project life cycle, constraints and risk management.
2
Describe project roles and responsibilities.
3
Plan a project using Gantt charts, CPA and PERT.
4
Monitor and control a project by stages and by exception.
STARTER
Building a bridge involves hundreds of tasks. How would you know which ones can't be allowed to slip?

## Slide 3
ENGINEERING CORE · Core topic 17
The project life cycle
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
3
Projects follow a life cycle. Initiation sets the brief, goals and success criteria. Planning works out resources, schedule and risks. Implementation does the work. Monitoring tracks progress against the plan. Reporting keeps stakeholders informed. Evaluation reviews what went well and what to improve.
Constraints include budget, cost, quality, time, safety, resources, communication, reputation and changing requirements. Risks are managed throughout.
Collaborative working, including matrix structures and shared digital tools, helps teams work together.
e.g.
EXAMPLE
Designing a new jig: the brief sets the target cycle time, the plan schedules design, manufacture and testing, and the evaluation records lessons for the next jig.

## Slide 4
ENGINEERING CORE · Core topic 17
The project life cycle
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
4
1
Initiate
Brief, goals and success criteria.
2
Plan
Resources, schedule, risks.
3
Implement
Do the work.
4
Monitor
Track against the plan.
5
Report
Keep stakeholders informed.
6
Evaluate
Review and learn.
Notes: Constraints: budget, cost, quality, time, safety, resources, communication, reputation, changing requirements. Collaborative working includes matrix working and collaborative technologies.

## Slide 5
ENGINEERING CORE · Core topic 17
Quick check: The project life cycle
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
5
1
What happens at initiation?
2
Name three project constraints.
3
Why evaluate a finished project?
Answer on mini whiteboards or in your book. Answers are in the speaker notes.
Notes: Answers:
1. The brief, goals and success criteria are set.
2. E.g. budget, time, quality.
3. To learn lessons for future projects.

## Slide 6
ENGINEERING CORE · Core topic 17
Roles
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
6
1
Stakeholders
Clients, regulators and others with an interest.
2
Project manager
Plans, monitors and controls the project.
3
Team members
Deliver the tasks and report progress.
4
Responsibilities
Communication, monitoring, planning, finance, reporting.

## Slide 7
ENGINEERING CORE · Core topic 17
Planning and control
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
7
Planning starts by identifying the resources needed: time, budget, people, training, communication and production facilities.
A Gantt chart shows tasks as bars on a timeline. Critical path analysis (CPA) finds the longest chain of dependent tasks, which sets the shortest possible project length. PERT uses optimistic, likely and pessimistic estimates. Contingency plans prepare for things going wrong.
Control uses monitoring reports on budget, quality, cost and time. Managing by stages approves each stage before the next; managing by exception escalates only when agreed limits are exceeded.
e.g.
EXAMPLE
Tasks: design 3 days, order parts 5, machine 4, assemble 2, test 1. If ordering can start during design, the critical path is order, machine, assemble, test: 12 days.

## Slide 8
ENGINEERING CORE · Core topic 17
Planning and control
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
8
Planning tools
Gantt charts: tasks on a timeline
Critical path analysis: the longest chain of dependent tasks
PERT: optimistic, likely and pessimistic estimates
Contingency planning and managing interdependencies
Control methods
Monitoring reports: budget, quality, cost, time
Managing by stages: approve each stage before the next
Managing by exception: escalate only when limits are exceeded

## Slide 9
ENGINEERING CORE · Core topic 17
Quick check: Planning and control
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
9
1
What does the critical path determine?
2
What is managing by exception?
3
What does PERT use?
Answer on mini whiteboards or in your book. Answers are in the speaker notes.
Notes: Answers:
1. The shortest possible project length.
2. Escalating only when limits are exceeded.
3. Optimistic, likely and pessimistic time estimates.

## Slide 10
ENGINEERING CORE · Core topic 17
Check your understanding
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
10
1
What happens if a critical path task is delayed?
2
What is managing by exception?
3
What does PERT use for time estimates?
4
Name three project constraints.
Notes: Give students a few minutes to answer on mini whiteboards or paper, then reveal the answers on the next slide.

## Slide 11
ENGINEERING CORE · Core topic 17
Answers
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
11
1
What happens if a critical path task is delayed?
The whole project is delayed.
2
What is managing by exception?
Only escalating issues when agreed tolerances are exceeded.
3
What does PERT use for time estimates?
Optimistic, most likely and pessimistic estimates.
4
Name three project constraints.
Any three, e.g. budget, time, quality.
Notes: Talk through any answers the class found difficult.

## Slide 12
ENGINEERING CORE · Core topic 17
Activity: Plan a workshop project
Design and Development for Engineering and Manufacturing T Level · Project and Programme Management
12
30 minutes
Pairs
1
Tasks: design (3 days), order parts (5), machine parts (4), assemble (2), test (1). Machining can't start until parts arrive.
2
Draw a Gantt chart.
3
Find the critical path and total duration.
4
Write one contingency plan.
SUCCESS CRITERIA
Dependencies correct
Critical path identified
Contingency is realistic
Notes: If ordering can start during design, the path is order, machine, assemble, test = 12 days; if it waits for design, 15 days. Discuss both.

## Slide 13
ENGINEERING CORE · Core topic 17
Exit ticket
1
Why involve regulators as stakeholders?
2
What is float?
3
When would you manage by stages?
REVISE THIS TOPIC
Revision notes for this lesson are on the study wiki:
Engineering Core, Part 2
https://lana6478.github.io/T-level-Design-Development-Engineering-Manufacturing/#/01-core-component/02-engineering-core-part2.md
Notes: Students answer on a sticky note or in the chat before leaving.